## Sheet1
	Date	Problem/todo	Status	Finished on

50	25/3/17	check other issues with renaming. e.g. class attributes renaming
49	25/3/17	Rename is not taking into consideration when analysing different versions of a feature: this includes, naturally, copy and twin
48	24/3/17	check different version of default_create: it should take the most recent version
47	23/03/17	https://drive.google.com/open?id=0B1GMHm59JFjqd0oxQjJranR0LWc
46	23/3/17	:= -> override
45	23/3/17	Precursor: crashes	Done	24/3/17
44	23/3/17	check cond and loop when doing create
43	23/3/17	Recursion: is it working in all cases?
42	23/3/17	V_LINKED_LIST_ITERATOR – index: probably the problem is that 'c' has Void as object	done: the problem was handling void ALIAS_OBJECTS	26/3/17
41	20/3/17	If attached x as xx then a:=xxend should not take into consideration the case of x being Void
40	18/3/17	subsume inside condition does not update conditional to restore the graph once finished	Done: functionality was added	23/3/2017
39	18/3/17	Local variables in case of loop inside cond (check also a cond inside a loop)	Done: treating local variables (apart of Result) was not being handled.	18/3/17
38	14/03/17	entity defined as att is_basic as argument is_basic as local not is_basic
37	14/3/17	String: hack -- classes: TYPE, ISE_ROUTINE, INTERNAL	Done: whenever something of the form v.w where 'v' is of type STRING, the implemenation does not check it (same as with basic types.	24/3/17
36	14/3/17	Agents
35	14/3/17	default_create	Done: when needed, the tool analysis the corresponding creation procedure	23/3/17
34	14/3/17	Inheritance	Initial implementation is done. Some crashes when try all cluster (needs to be checked). See also (47)	24/3/17
33	14/3/17	ANY: twin, copy, deep_twin, deep_copy	twin and copy being handled: there's a need for deep_twin and deep_copy implementation	24/3/17
32	14/3/17	Run cluster mml: there are some problems
31	8/3/17	check: Result := Result.x
30	8/3/17	remove scope of ALIAS_graph: not being used	Done	23/3/17
29	8/3/17	check: loop and recursion with new implementation
28	8/3/17	check: make do create a.make end
27	8/3/17	Eiffel Build
26	5/3/17	Other external features: ANY
25	5/3/17	items in SPECIAL has several ANY links. ToDo: to add only if needed	Done: hack was added	14/3/17
24	5/3/17	Local variables: In case of expanded type, they should have an initial object in the graph	Done: whenever used if they do not have a value, the implementation will give it to it	5/3/17
23	05/03/17	Handle detachable attributes. They should also have as initial value a Void reference. How to get detachable atts
22	4/3/17	V_ARRAY [G] (probably others as well) check what happens if G is expanded. e.g. V_ARRAY [INTEGER]
21	4/3/17	External: does not need to have note clause	Done	4/3/17
20	23/2/17	class_atts is always before update_atts. They both do the same and it is not necessary to do it twice. Check if this is true, if so, correct	Done: I removed update_att. The implementation always updates all class attributes when pushed things to the stack	5/3/17
19	23/02/17	Issues to directly analyse an external feature. No problems if the feature is being called	Done	4/3/17
18	21/02/2017	Check constants	Do not have any problem	14/3/17
17	21/02/2017	Class SPECIAL for hack: see sheet SPECIAL	Done: added `external_alias' note clause	03/04/17
16	20/02/17	Think about redefined features	It is the union of the feature to tackle dynamic binding	14/03/17
15	20/02/17	Should we analyse functions which return an expanded type?
14	20/02/2017	Agents: not supported?	They are not supported. I mention the issue in another cell. In March 14	14/03/17
13	20/02/2017	copy in ARRAY2: does nothing since 'external''s aliases have not been defined yet	Done: external features are being handled	05/03/17
12	20/02/2017	item in VARRAY2: crashes	Fixed: problem with path in conditionals	8/3/17
11	19/02/17	Empty feature fails	Done: problem was on the GUI part	19/02/17
10	19/02/17	What to do with arguments of feature being analysed? Should we output them?	Question
9	19/02/17	{V_DEFAULT}.default_value creates a default values for types. In case there is not it creates a new (unutilised) object	Hacked: it uses too much of the internal tricks. It could be easily hacked since it creates a new object: for the alias analysis, there is no need to go down since the result is known.	19/02/17
8	19/02/17	Print → should be ignore	Done	19/02/17
7	19/02/17	create: in cond, loop, recursion
6	19/02/17	What to do with once routines? Treat them as attributes after the first analysis?
5	19/02/17	x := f.d; f: T do create Result end	Done	19/02/17
4	19/02/17	once features	Working	19/02/17
3	19/02/17	class INTERNAL: can we hack it? We know it. (also REFLECTOR CLASS)
2	19/02/17	Class to hack: SPECIAL – TYPE – ISE_RUNTIME: they are all defined as external
1		No supported: t := {G}	Solved	19/02/17

## SPECIAL
note:	It could've been managed from the class by putting extra information (in a 'note' clause) to the class (as suggested by BM) however the class does not belong to Base2. TODO: to edit the class SPECIAL					make_empty
				count		no aliasing according to the postcondition	Hack in get_alias_info>ACCESS_FEAT_AS>find_routine>conditional

	Action: we subsume all items of the SPECIAL [G] by G ->_items

	Features
		name	External	Analysis	Action
		make_empty	Y	no aliasing according to the postcondition	subsume (items, all_items)
		count	Y	no aliasing according to the postcondition
		item	Y		alias (Result, items)	alias: [Result,items]
		put	Y	postcondition 'inserted' shows an alias: item (I) = v	An addition: alias (items, v)	alias: [v,items]
		fill_with	N		An addition: alias (items, v)	alias: [v,items]
		make_filled	N		New → Alias (all_items, v) subsume (items, all_items)	alias: [items,-]
		make_from_native_array	N	Does nothing	nothing
		at	N	calls item	alias (Result, items)	alias: [Result,items]
		index_of	N	Function returning Basic Type	nothing
		item_address	N	Function returning Basic Type	nothing
	check	base_address	Y		alias (Result, a_pointer)
		native_array	N	creates a new NATIVE_ARRAY	alias (Result, fresh(NATIVE_ARRAY))	alias: [Result,+ NATIVE_ARRAY]
	check	to_array	N
		index_set	N		alias (Result, fresh (INTEGER_INTERVAL))	alias: [Result,+ INTEGER_INTERVAL]
		lower	N	Basic Type constant	no alias
		upper	N	Basic Type attribute	no alias
		capacity	Y	Function returning Basic Type	no alias
		filled_with	N	Function returning Basic Type	no alias
		same_items	N	Function returning Basic Type	no alias
		valid_index	N	Function returning Basic Type	no alias
		force	N	Does 'put' or 'extend'	alias (items, v)	alias: [v,items]
		extend	Y	Similar postcondition as 'put'	alias (items, v)	alias: [v,items]
		extend_filled	N	Calls 'fill_with'	alias (items, v)	alias: [v,items]
		fill_with_default	N		alias (items, {T}.default)	alias: [v,items]
		insert_data	N		alias (items, other.items)
		copy_data	N	similar to insert but does not change the size	alias (items, other.items)
		move_data	N	it is being done by the initial submission	no alias
		overlapping_move	N	it is being done by the initial submission	no alias
		non_overlapping_move	N	it is being done by the initial submission	no alias
		keep_head	N		no alias
		keep_tail	N		no alias
		remove_head	N		no alias
		remove_tail	N		no alias
		resized_area	N		alias (Result.items, Current.items)
		resized_area_with_default	N	similar to resize_area	alias (Result.items, Current.items)
		aliased_resized_area	Y		alias (Result.items, Current.items)
		aliased_resized_area_with_default		Similar to aliased_resized_area	alias (Result.items, Current.items)
		replace_all	N		New (get rid of the other links) alias (items, v)
		wipe_out	N		Get ride of the links → subsume
		clear_all	N		Get ride of the links → subsume
	check	do_all_in_bounds	N
	check	do_if_in_bounds	N
	check	there_exists_in_bounds	N
	check	for_all_in_bounds	N
	check	do_all_with_index_in_bounds	N
	check	do_if_with_index_in_bounds	N
		element_size	Y	Function returning Basic Type
	check	set_count